## README
KenTender Comprehensive Test Plan Workbook
Comprehensive functional, control, security, integration, and UAT test planning workbook aligned to the current KenTender modular design.
Purpose | Provide a comprehensive KenTender test plan workbook covering the full modular public procurement lifecycle from Strategy and Budget through Requisition, Planning, Tendering, Bid Management, Award, Contract, Inspection, Complaints, Stores, Assets, and cross-cutting controls.
How to use | Start with Role_Catalogue, Journey_Catalogue, and Coverage_Matrix. Load the required seed pack(s), execute detailed scenarios from Test_Cases, record actual execution in UAT_Run_Log, and raise issues in Defect_Log.
Coverage | 173 detailed test cases across 7 phase bands and 23 business/security roles; 53 cases are marked Critical.
Execution sequencing | 1) Role/security smoke by persona; 2) Strategy & Budget; 3) Requisition; 4) Planning & Tendering; 5) Bid/Open/Evaluate/Award; 6) Contract & Inspection; 7) Complaints, Stores, Assets; 8) Cross-phase traceability and regression.
Entry criteria | Workflows, roles, field permlevels, user permissions, workspace routing, notification templates, supplier portal, protected file access, and representative seed data are configured in QA/UAT.
Exit criteria | All Critical cases passed; no unresolved blocker defects in lifecycle-critical paths; UAT seed packs and reset commands verified; audit and traceability checks completed.
Seed packs used | BASE-REF, BASE-STRAT, BASE-BUD, SP1 Requisition, SP2 Planning/Tender Prep, SP3 Bid/Opening, SP4 Evaluation/Award, SP5 Contract/Inspection, SP6 Complaint/Hold, SP7 Stores/Assets.

## Role_Catalogue
Role Catalogue
Primary roles, responsibilities, workspace focus, and core negative tests.
Role | Primary Workspaces | Primary Modules | Primary Responsibilities | Security Focus | Key Negative Tests
Planning Authority | Strategy & Planning | Strategy & Budget | Activate national/entity strategy structures; own strategic alignment rules | Can create/activate reference strategy data but must not approve downstream requisitions, awards, or contracts | Attempt downstream transactional approval should be blocked
Strategy Manager | Strategy & Planning | Strategy & Budget | Maintain entity strategic plans, programs, indicators and targets | Cross-entity hierarchy edits must be blocked | Attempt to link target from another entity should fail
Budget Officer | Budget Control | Strategy & Budget | Manage periods, budgets, budget lines, revisions and availability | Can view/post within allowed scope only; no tender or award approval authority | Cannot see other-entity budget lines without central scope
Finance Approver | My Work / Budget Control | Strategy & Budget; Requisitions; Contract Variations | Review financial posture, validate funds, approve finance steps | Cannot override hard-stop controls without approved exception | Attempt over-budget approval should fail
Requisitioner | My Work / Procurement Operations | Purchase Requisition | Create, edit draft, and resubmit returned requisitions | Must not see finance-only or approval-only fields | Cannot self-approve or directly edit approved requisitions
Head of Department | My Work / Procurement Operations | Purchase Requisition | Approve, reject, or return department requisitions | Can only act on departmental queue | Cannot approve own-originated requisition
Procurement Officer | Procurement Operations / Contract & Delivery | Planning; Tendering; Contracts | Consolidate demand, manage tender drafts, manage contract drafts | Cannot finalize awards or access sealed bids before opening | Attempt to publish unapproved tender should fail
Head of Procurement | Procurement Operations / Evaluation & Award | Tendering; Award Review; Contracts | Approve tender steps, review awards, oversee procurement decisions | Cannot use deliberations to bypass formal approvals | Attempt to finalize award without accounting officer should fail
Supplier Registration Officer | Procurement Operations | Supplier Registration & Compliance | Review supplier applications, compliance documents and activation | Cannot access bidder sealed content or evaluation internals | Suspended suppliers must remain blocked from tender actions
Opening Committee Chair | My Work / Procurement Operations | Bid Opening | Validate preconditions and execute opening sessions | Opening authority is assignment-based and time-gated | Unassigned user cannot execute opening
Opening Committee Member | My Work / Procurement Operations | Bid Opening | Attend opening and view register after opening | Cannot execute opening unless explicitly allowed | Pre-opening content access must be denied
Evaluation Committee Member | My Work / Evaluation & Award | Evaluation | Score assigned bids and submit evaluation records | Access requires assignment and conflict clearance | Cannot see unrelated evaluations or approve awards
Evaluation Committee Chair | Evaluation & Award | Evaluation; Recommendation | Manage stage progression and submit evaluation report | Must not silently alter submitted evaluator records | Cannot approve final award for same tender
Accounting Officer | My Work / Evaluation & Award | Award & Approval | Provide final award approval and selected contract authority steps | Must be final authority separate from evaluators | Deviation from recommendation requires deviation record
Contract Manager | Contract & Delivery | Contracts; Execution | Track milestones, deliverables, and variation requests | Cannot alter controlled commercial terms directly | Value/date changes require approved variation
Inspection Officer | Contract & Delivery | Inspection & Acceptance | Conduct inspections, capture evidence, raise non-conformance | May not activate contracts or waive critical failures without authority | Full acceptance blocked on critical unresolved NCR
Complaint Review Chair | Governance & Complaints | Complaints & Appeals | Admissibility, hold decisions, final complaint decisions | Must not be conflicted with challenged action | Cannot release hold outside complaint decision workflow
Complaint Review Member | My Work / Governance & Complaints | Complaints | Review evidence and submit review notes | Access only to assigned complaints | Cannot issue final decision
Storekeeper | Stores | Stores Management | Receive accepted goods, issue stores items, reconcile balances | Cannot register assets or edit procurement approvals | Attempt asset registration should fail
Asset Officer | Assets | Asset Management | Register, hand over, and move procured assets | Cannot receive goods into stores without stores role | Attempt goods receipt creation should fail
Auditor / Oversight User | Audit & Oversight | Cross-cutting oversight | Review audit events, exceptions, deviations, complaints and controls | Read-heavy access; no transactional mutation | Posting/approval actions should be blocked
System Administrator | Administration | Platform Configuration | Maintain master data, roles, templates, guard rules and system configuration | Must not be used as proxy business actor for UAT | Sensitive access remains controlled and audited
Supplier User | Supplier Portal | Tendering; Bid; Complaints; Signing | View eligible tenders, submit bids, file complaints, sign contracts where allowed | Can only see own supplier records and notifications | Cannot access competitor bids or internal deliberations

## Test_Strategy
Test Strategy
Execution model, entry/exit criteria, and data design for comprehensive functional, control, security, and UAT testing.
Objectives | Validate KenTender end-to-end business rules, role security, workflow authority, field-level restrictions, row-level permissions, auditability, notifications, workspace routing, and traceability across Strategy, Budget, Requisition, Planning, Tendering, Bid Management, Award, Contract, Inspection, Complaints, Stores, and Assets.
Test layers | 1. Role and access control 2. Module functional tests 3. Negative/control tests 4. Integration and document lineage 5. Audit, reporting, and transparency controls 6. Workspace/UAT journey validation 7. Regression after fixes
Primary environments | DEV for engineering verification; QA for controlled feature validation; UAT for role-based business acceptance using seeded users and scenario packs.
Entry criteria | Wave 0/1 foundation installed; relevant module stories deployed; roles and user permissions configured; workspaces available; notifications configured for test mode; representative seed data loaded; sensitive file access controls enabled.
Exit criteria | All Critical test cases passed; all High severity defects closed or accepted with waiver; no blocker defects in lifecycle-critical flows; seed packs and reset commands verified; audit and traceability checks pass.
Execution order | 1) Security smoke by persona 2) Phase 1/1.5 functional checks 3) Planning and tender readiness 4) Bid, opening, evaluation and award 5) Contract and inspection 6) Complaints, stores, assets 7) Cross-phase traceability and regression
Data strategy | Use deterministic baseline packs (BASE-REF, BASE-STRAT, BASE-BUD) plus scenario packs SP1-SP7. Reuse stable business IDs so defects are reproducible.
Defect severity model | Critical = blocks legal control or end-to-end progression; High = major functional/security defect; Medium = important but workaround exists; Low = cosmetic/reporting/UX issue.
Evidence standard | Capture screenshots, business IDs, timestamps, audit references, notification evidence, and seeded pack name for every executed UAT case.
Automation guidance | Automate high-risk service and workflow checks first: budget controls, sealed bids, opening, evaluation access, award deviation, complaint hold, contract activation, and inspection tolerance logic.

## Journey_Catalogue
Journey Catalogue
Named end-to-end business journeys used for role-based UAT and regression.
Journey ID | Phase | Journey | Personas | Seed Pack | Preconditions | Expected Outcome | Priority
AT-REQ-001 | Phase 1.5 | Submit and approve requisition | Requisitioner; Head of Department; Finance Approver; Procurement Officer | SP1 | Active strategy/budget seed pack loaded | Requisition approved, budget reserved, planning queue updated | Critical
AT-REQ-002 | Phase 1.5 | Return and resubmit requisition | Head of Department; Requisitioner | SP1 | Submitted requisition exists | Return history preserved; resubmission succeeds | High
AT-PLAN-001 | Phase 2 | Convert approved demand into procurement plan | Procurement Officer | SP2 | Approved requisitions available for planning | Plan created with source links and consolidation traceability | Critical
AT-TDR-001 | Phase 2 | Create and publish tender | Procurement Officer; Head of Procurement | SP2/SP3 | Plan item ready for tender; tender package completed | Tender published and visible to eligible suppliers | Critical
AT-BID-001 | Phase 3 | Supplier bid submission and receipt | Supplier User | SP3 | Published tender open for submission | Bid submitted, locked, and receipt issued | Critical
AT-OPEN-001 | Phase 3 | Execute bid opening | Opening Committee Chair; Opening Committee Member | SP3 | Scheduled session and active submitted bids exist | Bids opened atomically and register locked | Critical
AT-EVAL-001 | Phase 3 | Evaluate bids and submit report | Evaluation Committee Members; Evaluation Chair | SP4 | Opening completed; evaluator assignments exist | Scoring locked; evaluation report submitted | Critical
AT-AWD-001 | Phase 3 | Final award approval and standstill | Head of Procurement; Accounting Officer | SP4 | Submitted evaluation report exists | Award approved, notifications generated, standstill created | Critical
AT-CON-001 | Phase 4 | Create, sign, and activate contract | Procurement Officer; Supplier User; Contract Manager | SP5 | Award ready for contract | Contract signed and activated with milestones available | Critical
AT-INSP-001 | Phase 4 | Parameter-based inspection and acceptance | Inspection Officer; Contract Manager | SP5 | Active contract and inspection template exist | Parameters evaluated, NCR/acceptance path enforced | Critical
AT-CMP-001 | Phase 5 | Complaint submission and hold | Supplier User; Complaint Review Chair; Complaint Review Member | SP6 | Award in standstill and supplier eligible to complain | Complaint registered, hold applied/released via controlled decision | Critical
AT-STORES-001 | Phase 5 | Receive accepted goods into stores | Storekeeper | SP7 | Accepted goods output exists | Goods receipt and stores traceability recorded | High
AT-ASSET-001 | Phase 5 | Register procured asset and assign custody | Asset Officer | SP7 | Assetizable accepted/store-linked item exists | Asset source traceability and custody assignment preserved | High

## Test_Cases
Detailed Test Cases
Filter by phase, module, role, priority, or seed pack to execute focused cycles. Execution columns are left blank for UAT logging.
Test ID | Phase | Module | Submodule | Role | Priority | Type | Automation Candidate | Data Set | Permlevel Focus | Title | Preconditions | Steps | Expected Result | References | Execution Status | Actual Result | Tester | Execution Date | Defect ID
P1-001 | Phase 1 | Strategy & Budget | National Framework | Planning Authority | High | Functional | Candidate | BASE-STRAT | 0/1 | Create and activate National Framework | Planning Authority user has access to strategic masters | 1. Open Strategy & Planning. 2. Create National Framework record. 3. Set active period and lock reference. 4. Activate. | Framework saves, activates, and becomes selectable for entity plans. | FSD 3.1 / AT-STRAT-001 | Not Run
P1-002 | Phase 1 | Strategy & Budget | National Framework | Planning Authority | Critical | Control | Candidate | BASE-STRAT | 0/1 | Block overlapping active national framework version | One active framework exists for the same scope | 1. Attempt to create or activate a second overlapping version. 2. Save/activate. | System blocks overlap and records validation/audit event. | FSD 3.1 | Not Run
P1-003 | Phase 1 | Strategy & Budget | Entity Strategic Plan | Strategy Manager | High | Functional | Candidate | BASE-STRAT | 0/1 | Create Entity Strategic Plan linked to National Framework | Active National Framework exists | 1. Create entity strategic plan. 2. Link procuring entity and primary national framework. 3. Save. | Entity plan is created with valid hierarchy context. | FSD 3.1 | Not Run
P1-004 | Phase 1 | Strategy & Budget | Program & Sub-program | Strategy Manager | High | Functional | Candidate | BASE-STRAT | 0 | Create Program and Sub-program hierarchy | Entity Strategic Plan exists | 1. Add Program. 2. Add Sub-program under Program. 3. Save. | Program and Sub-program inherit correct entity and plan. | FSD 3.1 | Not Run
P1-005 | Phase 1 | Strategy & Budget | Indicators & Targets | Strategy Manager | High | Functional | Candidate | BASE-STRAT | 0 | Create Output Indicator and Performance Target | Entity strategy hierarchy exists | 1. Create Output Indicator. 2. Create Performance Target for current FY. 3. Save. | Indicator and target are valid for downstream budget and requisition linkage. | FSD 3.1 | Not Run
P1-006 | Phase 1 | Strategy & Budget | Strategic Validation | Planning Authority | Critical | Negative | Candidate | BASE-STRAT | 0/1 | Block cross-entity strategy linkage | Two entities exist | 1. Attempt to link Program from Entity A to Target from Entity B. 2. Save. | System blocks invalid cross-entity linkage. | FSD 3.1 | Not Run
P1-007 | Phase 1 | Strategy & Budget | Budget Control Period | Budget Officer | High | Functional | Candidate | BASE-BUD | 0/1 | Create Budget Control Period | Entity and fiscal year exist | 1. Create Budget Control Period. 2. Mark as open/active. 3. Save. | Control period is created and available for budget header creation. | FSD 3.2 | Not Run
P1-008 | Phase 1 | Strategy & Budget | Budget Control Period | Budget Officer | Critical | Control | Candidate | BASE-BUD | 0/1 | Block second open Budget Control Period for same entity/FY | One open control period exists | 1. Attempt to create another open period. 2. Save. | System blocks duplicate open period. | FSD 3.2 | Not Run
P1-009 | Phase 1 | Strategy & Budget | Budget Header | Budget Officer | High | Functional | Candidate | BASE-BUD | 0/1 | Create Budget header version | Open control period exists | 1. Create Budget header. 2. Link entity and control period. 3. Save. | Budget header is created with versioning fields. | FSD 3.2 | Not Run
P1-010 | Phase 1 | Strategy & Budget | Budget Lines | Budget Officer | High | Functional | Candidate | BASE-BUD | 0/1 | Create valid Budget Line with strategy mapping | Budget header and strategy hierarchy exist | 1. Create Budget Line. 2. Link funding source, program, indicator, target. 3. Save. | Budget Line saves with valid strategic and entity alignment. | FSD 3.2 | Not Run
P1-011 | Phase 1 | Strategy & Budget | Budget Lines | Budget Officer | Critical | Negative | Candidate | BASE-BUD | 0/1 | Block Budget Line with invalid strategy hierarchy | Budget header exists | 1. Create Budget Line. 2. Link mismatched Sub-program and Target. 3. Save. | System rejects invalid strategy combination. | FSD 3.2 | Not Run
P1-012 | Phase 1 | Strategy & Budget | Budget Availability | Budget Officer | High | Integration | Candidate | BASE-BUD | 1 | Calculate budget availability from authoritative ledger | Budget line and ledger entries exist | 1. Open budget availability view. 2. Compare allocated, reserved, committed and available values. | Availability matches ledger-derived values. | FSD 3.2 | Not Run
P1-013 | Phase 1 | Strategy & Budget | Budget Reservation | Finance Approver | Critical | Control | Candidate | BASE-BUD | 1/2 | Reserve budget within available balance | Healthy budget line exists | 1. Trigger reservation through service path. 2. Check ledger entries. | Reservation posts append-only ledger entry and updates availability. | FSD 3.2 | Not Run
P1-014 | Phase 1 | Strategy & Budget | Budget Reservation | Finance Approver | Critical | Negative | Candidate | BASE-BUD | 1/2 | Block reservation beyond available balance | Constrained budget line exists | 1. Attempt reservation above available. 2. Observe response. | Reservation is blocked; no ledger entry posts. | FSD 3.2 | Not Run
P1-015 | Phase 1 | Strategy & Budget | Reservation Release | Finance Approver | High | Integration | Candidate | BASE-BUD | 1/2 | Release reservation through reversal-style movement | Budget reservation already exists | 1. Trigger reservation release. 2. Inspect resulting ledger entries. | Release posts reversal-style entry; prior posted entries remain intact. | FSD 3.2 | Not Run
P1-016 | Phase 1 | Strategy & Budget | Commitment Control | Finance Approver | High | Integration | Candidate | BASE-BUD | 1/2 | Commit budget after upstream approval state | Reservation exists | 1. Trigger commit. 2. Inspect ledger and availability. | Commitment entry posts correctly and availability updates. | FSD 3.2 | Not Run
P1-017 | Phase 1 | Strategy & Budget | Idempotency | Finance Approver | Critical | Control | Candidate | BASE-BUD | 2 | Prevent duplicate reservation on retried request | Same request context used twice | 1. Trigger reservation. 2. Retry same request idempotently. | Only one effective reservation is retained or duplicate is blocked safely. | FSD 3.2 | Not Run
P1-018 | Phase 1 | Strategy & Budget | Budget Revision | Budget Officer | High | Functional | Candidate | BASE-BUD | 1/2 | Apply budget revision increasing line amount | Budget revision object exists | 1. Create/apply revision. 2. Re-open availability. | Revised budget line reflects approved increase with audit trail. | FSD 3.2 | Not Run
P1-019 | Phase 1 | Strategy & Budget | Budget Revision | Budget Officer | Critical | Negative | Candidate | BASE-BUD | 1/2 | Block budget revision that cuts below active exposure | Existing reservations/commitments exceed revised amount | 1. Attempt downward revision. 2. Apply. | System blocks revision until exposure is resolved or exception approved. | FSD 3.2 | Not Run
P1-020 | Phase 1 | Strategy & Budget | Validation API | Budget Officer | Critical | Integration | Candidate | BASE-BUD | 1 | Validate funds using downstream API | Budget lines exist | 1. Call validation from downstream context. 2. Check result for healthy and constrained lines. | Validation service returns correct pass/fail outcome. | FSD 3.2 | Not Run
P1-021 | Phase 1 | Strategy & Budget | Security | Budget Officer | High | Security | Manual-first | BASE-BUD | 0/1 | Enforce entity scope on budget lines | Two entities exist with separate budget lines | 1. Log in scoped user. 2. Attempt to view other-entity lines. | Other-entity data is hidden or blocked by row permissions. | Phase 4 RBAC | Not Run
P1-022 | Phase 1 | Strategy & Budget | Security | Auditor / Oversight User | Medium | Security | Manual-first | BASE-BUD | 1/2 | Allow read-only oversight to auditor without posting rights | Auditor role exists | 1. Open budget records. 2. Attempt posting action. | Auditor can view but cannot reserve, release, or commit. | Phase 4 RBAC | Not Run
P1-023 | Phase 1 | Strategy & Budget | Numbering | System Administrator | Medium | Configuration | Candidate | BASE-REF | 0 | Generate business IDs using numbering policy | Reference Number Policy exists | 1. Trigger ID generation for strategy and budget objects. 2. Compare against pattern. | Business IDs follow approved pattern and scope rules. | Phase 4 / Wave 0 | Not Run
P1-024 | Phase 1 | Strategy & Budget | Master Data | System Administrator | Medium | Configuration | Manual-first | BASE-REF | 0 | Maintain Procurement Methods and Categories | Admin has access to core master data | 1. Create/activate category and method records. 2. Save. | Master records become selectable downstream and audit is captured. | Wave 0 Core | Not Run
P1-025 | Phase 1 | Strategy & Budget | Separation of Duty | Planning Authority | High | Security | Candidate | BASE-REF | 0/1 | Prevent planning authority from approving downstream requisitions | Planning Authority role exists | 1. Attempt downstream requisition approval using planning authority user. | Action is blocked by separation-of-duty rules. | Phase 4 RBAC | Not Run
P1-026 | Phase 1 | Strategy & Budget | Reporting | Budget Officer | Medium | Reporting | Candidate | BASE-BUD | 0 | Run budget exposure and availability report | Budget lines and ledger entries exist | 1. Open Budget Control workspace. 2. Run availability report. | Report shows accurate totals and negative conditions clearly. | FSD 3.2 / WS-003 | Not Run
P1-027 | Phase 1 | Strategy & Budget | Hard Stop Rules | Finance Approver | Critical | Control | Candidate | BASE-BUD | 1/2 | Enforce hard-stop budget line rule | Hard-stop line exists | 1. Attempt over-budget operation on hard-stop line. | System blocks action with clear reason and no partial post. | FSD 3.2 | Not Run
P1-028 | Phase 1 | Strategy & Budget | Audit | Auditor / Oversight User | High | Audit | Candidate | BASE-BUD | 1/2 | Capture audit event for budget reservation | Reservation action performed | 1. Open audit workspace. 2. Filter by budget reservation event. | Audit event includes actor, source object, amount and timestamp. | Phase 4 Audit | Not Run
P1-029 | Phase 1 | Strategy & Budget | Workspace | Budget Officer | Low | UX | Manual-first | BASE-BUD | 0 | Budget Control workspace surfaces the right queues | Workspace implementation exists | 1. Open Budget Control workspace. 2. Verify core shortcuts. | User sees periods, budgets, lines, revisions, and availability shortcuts only. | UAT Workspace Pack | Not Run
P1-030 | Phase 1 | Strategy & Budget | Seed Data | System Administrator | Low | Data | Manual-first | BASE-BUD | 0 | Reset BASE-STRAT and BASE-BUD deterministically | UAT seed commands exist | 1. Run baseline reset. 2. Verify key business IDs. | Baseline seed packs reload stable IDs and values. | UAT Seed Pack | Not Run
P15-001 | Phase 1.5 | Purchase Requisition | Creation | Requisitioner | High | Functional | Candidate | SP1 | 0 | Create standard requisition against valid budget line | Healthy budget line and target exist | 1. Open Procurement Operations. 2. Create requisition. 3. Add strategy and budget links. 4. Save draft. | Draft requisition is created with business ID and valid linkages. | FSD 3.3.1 / AT-REQ-001 | Not Run
P15-002 | Phase 1.5 | Purchase Requisition | Line Items | Requisitioner | High | Functional | Candidate | SP1 | 0 | Create multi-line requisition and derive total | Draft requisition exists | 1. Add multiple items. 2. Save. | Requested amount equals sum of line totals. | FSD 3.3.1 | Not Run
P15-003 | Phase 1.5 | Purchase Requisition | Emergency Path | Requisitioner | Critical | Control | Candidate | SP1 | 0/1 | Require emergency justification for emergency requisition | Draft requisition exists | 1. Tick emergency flag. 2. Leave justification blank. 3. Save/submit. | System blocks save/submit until justification is provided. | FSD 3.3.1 | Not Run
P15-004 | Phase 1.5 | Purchase Requisition | Approval Security | Head of Department | Critical | Security | Candidate | SP1 | 1/2 | Block requestor self-approval | Requestor and approver user are the same | 1. Submit requisition. 2. Attempt approval as same person. | Approval is blocked by separation-of-duty control. | FSD 3.3.1 | Not Run
P15-005 | Phase 1.5 | Purchase Requisition | Workflow | Head of Department | High | Functional | Candidate | SP1 | 1 | Approve requisition at HOD step | Submitted requisition awaits HOD | 1. Open Pending Requisition Approvals. 2. Review and approve. | Approval record is created and workflow moves forward. | FSD 3.3.1 | Not Run
P15-006 | Phase 1.5 | Purchase Requisition | Workflow | Head of Department | High | Functional | Candidate | SP1 | 1 | Return requisition for revision | Submitted requisition exists | 1. Open requisition. 2. Return for revision with comments. | Requisition becomes editable through return path and history is preserved. | FSD 3.3.1 / AT-REQ-002 | Not Run
P15-007 | Phase 1.5 | Purchase Requisition | Finance Review | Finance Approver | High | Functional | Candidate | SP1 | 1/2 | Review requisition budget posture at finance step | HOD-approved requisition exists | 1. Open assigned requisition. 2. Validate budget posture. 3. Approve. | Finance approval record is created and final approval route becomes available. | FSD 3.3.1 | Not Run
P15-008 | Phase 1.5 | Purchase Requisition | Budget Integration | Finance Approver | Critical | Integration | Candidate | SP1 | 1/2 | Reserve budget on final approval | Final approval route is available | 1. Complete final approval. 2. Inspect requisition budget fields and ledger. | Budget reservation is created through shared budget service and requisition status updates. | FSD 3.3.1 | Not Run
P15-009 | Phase 1.5 | Purchase Requisition | Budget Integration | Finance Approver | Critical | Negative | Candidate | SP1 | 1/2 | Block final approval when funds are insufficient | Constrained budget line requisition exists | 1. Attempt final approval. | Final approval is blocked and no reservation posts. | FSD 3.3.1 | Not Run
P15-010 | Phase 1.5 | Purchase Requisition | Edit Lock | Requisitioner | High | Control | Candidate | SP1 | 1 | Prevent direct edits to approved requisition | Approved requisition exists | 1. Open approved requisition. 2. Attempt to edit controlled fields. | Controlled fields are locked and edit is blocked outside amendment flow. | FSD 3.3.1 | Not Run
P15-011 | Phase 1.5 | Purchase Requisition | Amendments | Requisitioner | High | Control | Candidate | SP1 | 1/2 | Create amendment record for quantity change | Approved requisition exists | 1. Create amendment record. 2. Capture before/after summary. | Amendment record is created for approval/apply path. | FSD 3.3.1 | Not Run
P15-012 | Phase 1.5 | Purchase Requisition | Amendments | Procurement Officer | High | Integration | Candidate | SP1 | 1/2 | Apply approved amendment and adjust reservation | Approved amendment exists | 1. Apply amendment. 2. Inspect requisition and budget status. | Requisition updates through service path and budget adjustment/release is triggered as needed. | FSD 3.3.1 | Not Run
P15-013 | Phase 1.5 | Purchase Requisition | Cancellation | Procurement Officer | Critical | Control | Candidate | SP1 | 1/2 | Cancel approved requisition and release reservation | Approved requisition with reservation exists | 1. Cancel requisition using controlled action. | Reservation is released and requisition is not planning-eligible. | FSD 3.3.1 | Not Run
P15-014 | Phase 1.5 | Purchase Requisition | Planning Linkage | Procurement Officer | High | Integration | Candidate | SP1 | 0/1 | Derive planning status as Not Planned | Approved requisition has no planning links | 1. Open requisition. | Planning status is Not Planned with full unplanned amount. | FSD 3.3.1 | Not Run
P15-015 | Phase 1.5 | Purchase Requisition | Planning Linkage | Procurement Officer | High | Integration | Candidate | SP2 | 0/1 | Derive planning status as Partially Planned | Requisition has partial planning link | 1. Open requisition linked to one partial plan item. | Planning status is Partially Planned with correct planned/unplanned amounts. | FSD 3.3.1 | Not Run
P15-016 | Phase 1.5 | Purchase Requisition | Planning Linkage | Procurement Officer | High | Integration | Candidate | SP2 | 0/1 | Derive planning status as Fully Planned | Requisition fully linked into procurement plan | 1. Open requisition. 2. Review planning summary. | Planning status is Fully Planned or Converted to Plan. | FSD 3.3.1 | Not Run
P15-017 | Phase 1.5 | Purchase Requisition | Queue Views | Requisitioner | Medium | UX | Manual-first | SP1 | 0 | My Requisitions queue shows only own records | Multiple requisitions exist across users | 1. Log in as requisitioner. 2. Open My Requisitions. | User sees own requisitions only with correct statuses. | WS-004 / UAT Workspace Pack | Not Run
P15-018 | Phase 1.5 | Purchase Requisition | Queue Views | Head of Department | Medium | UX | Manual-first | SP1 | 0 | Pending Requisition Approvals shows HOD work queue | Submitted requisitions exist | 1. Open Pending Requisition Approvals. | Queue shows only items awaiting HOD action. | WS-004 / UAT Workspace Pack | Not Run
P15-019 | Phase 1.5 | Purchase Requisition | Field Security | Requisitioner | High | Security | Manual-first | SP1 | 1/2 | Hide finance-only fields from requestor | Finance fields exist on form | 1. Open requisition form as requestor. | Finance review/reservation fields are hidden or read-only per role. | Phase 4 RBAC | Not Run
P15-020 | Phase 1.5 | Purchase Requisition | Date Validation | Requisitioner | Medium | Negative | Candidate | SP1 | 0 | Block invalid required-by date earlier than request date | Draft requisition exists | 1. Enter required-by date before request date. 2. Save. | System blocks invalid date combination. | FSD 3.3.1 | Not Run
P15-021 | Phase 1.5 | Purchase Requisition | Structural Validation | Requisitioner | Critical | Negative | Candidate | SP1 | 0 | Block submission of requisition with no items | Draft requisition has no items | 1. Attempt to submit. | System blocks submission until at least one item exists. | FSD 3.3.1 | Not Run
P15-022 | Phase 1.5 | Purchase Requisition | Audit | Auditor / Oversight User | High | Audit | Candidate | SP1 | 1/2 | Audit trail records submit, approve, return and cancel actions | Requisition lifecycle actions have occurred | 1. Open Audit & Oversight. 2. Filter by requisition business ID. | All material requisition actions are visible with actor and timestamp. | Phase 4 Audit | Not Run
P15-023 | Phase 1.5 | Purchase Requisition | Emergency Exception | Finance Approver | High | Control | Manual-first | SP1 | 2 | Emergency requisition requires linked exception record when policy demands | Emergency path configured | 1. Approve emergency requisition. 2. Review exception reference. | Emergency requisition carries explicit exception/override record where configured. | FSD 3.3.1 | Not Run
P15-024 | Phase 1.5 | Purchase Requisition | Search & Reports | Procurement Officer | Low | Reporting | Candidate | SP1 | 0 | Planning-ready requisition report shows approved and unplanned demand | Approved requisitions exist | 1. Open Planning Ready Requisitions report. | Report lists approved unplanned requisitions with correct amounts. | WS-004 | Not Run
P15-025 | Phase 1.5 | Purchase Requisition | Reset/Data | System Administrator | Low | Data | Manual-first | SP1 | 0 | SP1 seed pack resets requisition scenarios deterministically | Seed commands exist | 1. Reset to SP1. 2. Verify key requisition IDs and statuses. | Requisition scenarios reload with known IDs and expected states. | UAT Seed Pack | Not Run
P2-001 | Phase 2 | Planning & Tendering | Procurement Plan | Procurement Officer | High | Functional | Candidate | SP2 | 0/1 | Create procurement plan for active control period | Entity, control period and approved demand exist | 1. Create Procurement Plan. 2. Save draft. | Plan is created with version and ownership fields. | FSD 3.3.2 / AT-PLAN-001 | Not Run
P2-002 | Phase 2 | Planning & Tendering | Procurement Plan | Planning Authority | High | Functional | Candidate | SP2 | 1 | Approve procurement plan through formal route | Draft plan exists | 1. Submit plan. 2. Review/approve. | Approval record is created and plan status advances. | FSD 3.3.2 | Not Run
P2-003 | Phase 2 | Planning & Tendering | Plan Items | Procurement Officer | High | Functional | Candidate | SP2 | 0 | Create plan item from approved requisition | Approved requisition exists | 1. Add requisition to plan. 2. Create plan item. | Plan item inherits source strategy/budget context. | FSD 3.3.2 | Not Run
P2-004 | Phase 2 | Planning & Tendering | Consolidation | Procurement Officer | High | Integration | Candidate | SP2 | 0/1 | Consolidate two similar requisitions into one plan item | Two compatible approved requisitions exist | 1. Select both requisitions. 2. Consolidate into one plan item. | Consolidation source records are created and linked amounts reconcile. | FSD 3.3.2 | Not Run
P2-005 | Phase 2 | Planning & Tendering | Consolidation | Procurement Officer | Critical | Negative | Candidate | SP2 | 0/1 | Block over-planning beyond requisition approved amount | Requisition already partially planned | 1. Attempt to link more than remaining amount. | System blocks over-planning and preserves prior links. | FSD 3.3.2 | Not Run
P2-006 | Phase 2 | Planning & Tendering | Fragmentation Control | Procurement Officer | High | Control | Candidate | SP2 | 1 | Generate fragmentation alert for suspicious split demand | Two similar plan items exist on same budget line | 1. Run fragmentation scan or save plan items. 2. Review alerts. | Plan Fragmentation Alert is created with severity and reason. | FSD 3.3.2 | Not Run
P2-007 | Phase 2 | Planning & Tendering | Fragmentation Control | Head of Procurement | High | Control | Manual-first | SP2 | 1/2 | Review and justify non-blocking fragmentation warning | Warning alert exists | 1. Open alert. 2. Enter review notes and justification. | Alert review is captured without silent deletion of the alert. | FSD 3.3.2 | Not Run
P2-008 | Phase 2 | Planning & Tendering | Manual Plan Items | Procurement Officer | High | Control | Candidate | SP2 | 1 | Require justification for manual strategic plan item | Manual items are allowed by policy | 1. Create manual item without justification. 2. Save/submit. | System blocks until manual-entry justification is provided. | FSD 3.3.2 | Not Run
P2-009 | Phase 2 | Planning & Tendering | Plan Revisions | Procurement Officer | High | Control | Candidate | SP2 | 1 | Create plan revision to add item mid-year | Approved plan exists | 1. Create plan revision. 2. Add revision line. 3. Save. | Revision record captures before/after context. | FSD 3.3.2 | Not Run
P2-010 | Phase 2 | Planning & Tendering | Plan Revisions | Procurement Officer | High | Integration | Candidate | SP2 | 1/2 | Apply approved plan revision | Approved revision exists | 1. Apply revision. 2. Review updated plan items and version context. | Revision is applied through service path and audit event is created. | FSD 3.3.2 | Not Run
P2-011 | Phase 2 | Planning & Tendering | Edit Lock | Procurement Officer | High | Control | Candidate | SP2 | 1 | Block direct edits to active plan without revision | Active plan exists | 1. Attempt direct edit to controlled fields. | System blocks edit and requires revision path. | FSD 3.3.2 | Not Run
P2-012 | Phase 2 | Planning & Tendering | Tender Gate | Procurement Officer | Critical | Control | Candidate | SP2 | 1 | Create tender only from approved active plan item | Approved active plan item exists | 1. Trigger Create Tender from plan item. | Tender draft is created with plan linkage and Plan-to-Tender link. | FSD 3.3.2 | Not Run
P2-013 | Phase 2 | Planning & Tendering | Tender Gate | Procurement Officer | Critical | Negative | Candidate | SP2 | 1 | Block tender creation from cancelled or ineligible plan item | Cancelled or draft plan item exists | 1. Attempt Create Tender. | System blocks tender creation and states reason. | FSD 3.3.2 | Not Run
P2-014 | Phase 2 | Planning & Tendering | Tender Draft | Procurement Officer | High | Functional | Candidate | SP3 | 0/1 | Tender draft inherits plan context | Tender draft created from plan item | 1. Open draft tender. 2. Review inherited fields. | Strategy, budget, amount and department context are inherited appropriately. | FSD 3.3.3 / AT-TDR-001 | Not Run
P2-015 | Phase 2 | Planning & Tendering | Tender Criteria | Procurement Officer | High | Functional | Candidate | SP3 | 0 | Add tender criteria before publication | Draft tender exists | 1. Add mandatory, technical and financial criteria. 2. Save. | Criteria are stored and available for evaluation later. | FSD 3.3.3 | Not Run
P2-016 | Phase 2 | Planning & Tendering | Tender Documents | Procurement Officer | High | Functional | Candidate | SP3 | 0 | Upload tender document set | Draft tender exists | 1. Add instructions, specifications, price schedule and draft contract. 2. Save. | Tender document registry captures files with types and sensitivity. | FSD 3.3.3 | Not Run
P2-017 | Phase 2 | Planning & Tendering | Publication Readiness | Head of Procurement | Critical | Control | Candidate | SP3 | 1/2 | Block publication until mandatory criteria and documents exist | Draft tender missing one required component | 1. Attempt publish. | Publication is blocked with clear readiness message. | FSD 3.3.3 | Not Run
P2-018 | Phase 2 | Planning & Tendering | Publication | Head of Procurement | Critical | Functional | Candidate | SP3 | 1/2 | Publish tender successfully | Approved tender with complete package exists | 1. Publish tender. | Publication timestamp is set; submission window opens and audit event is recorded. | FSD 3.3.3 | Not Run
P2-019 | Phase 2 | Planning & Tendering | Restricted Tender | Procurement Officer | High | Control | Candidate | SP3 | 1 | Require visibility rules for restricted/prequalified tender | Restricted tender type selected | 1. Leave visibility rules blank. 2. Attempt publish. | System blocks until supplier visibility/invitation basis exists. | FSD 3.3.3 | Not Run
P2-020 | Phase 2 | Planning & Tendering | Clarifications | Procurement Officer | Medium | Functional | Hybrid | SP3 | 0 | Publish clarification response to all eligible suppliers | Open clarification exists | 1. Respond to clarification. 2. Publish response. | All eligible suppliers see the same official response. | FSD 3.3.3 | Not Run
P2-021 | Phase 2 | Planning & Tendering | Amendments | Procurement Officer | High | Functional | Hybrid | SP3 | 1 | Issue tender amendment with deadline extension | Published tender exists | 1. Create amendment. 2. Extend submission deadline. 3. Publish. | Published amendment updates deadline and preserves original history. | FSD 3.3.3 | Not Run
P2-022 | Phase 2 | Planning & Tendering | Field Lock | Procurement Officer | High | Control | Candidate | SP3 | 1 | Prevent direct edit of published tender core fields | Published tender exists | 1. Attempt to change method or deadline directly on tender. | System blocks direct edit and requires amendment flow. | FSD 3.3.3 | Not Run
P2-023 | Phase 2 | Planning & Tendering | Supplier Eligibility | Supplier Registration Officer | High | Integration | Candidate | SP3 | 0/1 | Block suspended supplier from seeing or acting on restricted tender | Suspended supplier exists | 1. Log in as suspended supplier. 2. Attempt to view tender/submit bid. | Supplier is blocked based on eligibility status. | FSD 3.3.3 | Not Run
P2-024 | Phase 2 | Planning & Tendering | Supplier Portal | Supplier User | Medium | UX | Manual-first | SP3 | 0 | Show eligible tenders only in supplier portal | Multiple tenders with different visibility exist | 1. Open portal as supplier user. | User sees only eligible tenders and allowed documents. | UAT Workspace Pack | Not Run
P2-025 | Phase 2 | Planning & Tendering | Security | Procurement Officer | Critical | Security | Candidate | SP3 | 1/2 | Prevent unapproved tender from being published by procurement officer alone | Draft/unapproved tender exists | 1. Attempt publish without approval. | Publish action is blocked by workflow/guard rules. | FSD 3.3.3 | Not Run
P2-026 | Phase 2 | Planning & Tendering | Audit | Auditor / Oversight User | High | Audit | Candidate | SP3 | 1/2 | Capture publication and amendment audit trail | Tender publication/amendment performed | 1. Filter audit events by tender business ID. | Publication and amendment events are complete and attributable. | Phase 4 Audit | Not Run
P2-027 | Phase 2 | Planning & Tendering | Queues | Procurement Officer | Low | UX | Manual-first | SP2 | 0 | Planning Queue and Draft Tenders shortcuts show correct records | Relevant seeded data exists | 1. Open Procurement Operations workspace. 2. Check queue shortcuts. | Task queues show planning-ready requisitions, draft tenders, and opening sessions as designed. | WS-004 | Not Run
P3-001 | Phase 3 | Bid to Award | Bid Draft | Supplier User | High | Functional | Hybrid | SP3 | 0 | Start draft bid from supplier portal | Published tender visible to supplier | 1. Open tender. 2. Start draft bid. | Draft bid is created for supplier and tender. | FSD 3.3.4 / AT-BID-001 | Not Run
P3-002 | Phase 3 | Bid to Award | Bid Documents | Supplier User | High | Functional | Hybrid | SP3 | 0 | Upload required bid documents | Draft bid exists | 1. Upload required documents. 2. Save draft. | Documents attach to correct bid sections and remain draft state until final submit. | FSD 3.3.4 | Not Run
P3-003 | Phase 3 | Bid to Award | Bid Validation | Supplier User | High | Functional | Candidate | SP3 | 0 | Run bid validation before submit | Draft bid with docs exists | 1. Run validation. | Validation reports missing items or passes accordingly. | FSD 3.3.4 | Not Run
P3-004 | Phase 3 | Bid to Award | Final Submission | Supplier User | Critical | Functional | Candidate | SP3 | 1 | Submit final bid and receive receipt | Bid passes validation and deadline is open | 1. Submit final bid. 2. View receipt. | Bid becomes submitted/locked and receipt is generated. | FSD 3.3.4 | Not Run
P3-005 | Phase 3 | Bid to Award | Deadline Control | Supplier User | Critical | Negative | Candidate | SP3 | 1 | Block bid submission after deadline | Submission deadline has passed | 1. Attempt final submit. | Submission is blocked and no active receipt is generated. | FSD 3.3.4 | Not Run
P3-006 | Phase 3 | Bid to Award | Withdrawal | Supplier User | High | Functional | Candidate | SP3 | 1 | Withdraw submitted bid before deadline | Submitted bid exists and withdrawal allowed | 1. Trigger withdraw action. | Bid becomes withdrawn and is excluded from opening set. | FSD 3.3.4 | Not Run
P3-007 | Phase 3 | Bid to Award | Resubmission | Supplier User | High | Control | Candidate | SP3 | 1 | Create new active version on resubmission | Withdrawn bid exists and deadline still open | 1. Resubmit bid. 2. Review version history. | New active submission version exists and prior receipt is superseded, not overwritten. | FSD 3.3.4 | Not Run
P3-008 | Phase 3 | Bid to Award | Sealed Access | System Administrator | Critical | Security | Manual-first | SP3 | 2 | Prevent pre-opening access to sealed bid content | Submitted bid exists | 1. Attempt direct access to sealed attachment. 2. Review outcome. | Access is denied or tightly controlled and audit is captured. | FSD 3.3.4 / Phase 4 | Not Run
P3-009 | Phase 3 | Bid to Award | Opening Preconditions | Opening Committee Chair | Critical | Control | Candidate | SP3 | 1/2 | Validate opening preconditions before opening session | Scheduled session and bids exist | 1. Open session. 2. Run precondition check. | Precondition result shows candidate bids and blockers if any. | FSD 3.3.5 / AT-OPEN-001 | Not Run
P3-010 | Phase 3 | Bid to Award | Bid Opening | Opening Committee Chair | Critical | Functional | Candidate | SP3 | 1/2 | Execute opening and generate opening register | Preconditions pass | 1. Record attendance. 2. Execute opening. | Bids move from sealed to opened and register is generated/locked. | FSD 3.3.5 | Not Run
P3-011 | Phase 3 | Bid to Award | Opening Candidate Set | Opening Committee Chair | High | Control | Candidate | SP3 | 1/2 | Exclude withdrawn and superseded bids from opening set | Mix of active, withdrawn and superseded bids exists | 1. Execute opening. 2. Review register lines. | Only latest active submitted bids are opened; exclusions are recorded transparently. | FSD 3.3.5 | Not Run
P3-012 | Phase 3 | Bid to Award | Opening Security | Opening Committee Member | High | Security | Manual-first | SP3 | 1/2 | Allow assigned committee members to view register after opening only | Opening completed | 1. Log in as assigned member. 2. Open register. | Assigned member can view register after opening but could not pre-open content. | FSD 3.3.5 | Not Run
P3-013 | Phase 3 | Bid to Award | Opening Authority | Procurement Officer | Critical | Security | Candidate | SP3 | 1/2 | Block unassigned procurement user from executing opening | Opening session exists | 1. Attempt Execute Opening as non-chair/unassigned user. | Action is blocked by assignment/role rules. | FSD 3.3.5 | Not Run
P3-014 | Phase 3 | Bid to Award | Conflict Declaration | Evaluation Committee Member | Critical | Control | Candidate | SP4 | 1 | Require conflict declaration before evaluation access | Assigned evaluation exists | 1. Attempt to open evaluation without declaration. | Access is blocked until conflict declaration is completed. | FSD 3.3.6 | Not Run
P3-015 | Phase 3 | Bid to Award | Evaluation Access | Evaluation Committee Member | High | Security | Candidate | SP4 | 1 | Show evaluator only assigned evaluation session | Multiple evaluation sessions/users exist | 1. Log in as evaluator. 2. Open My Assigned Evaluations. | Evaluator sees only assigned session(s). | FSD 3.3.6 | Not Run
P3-016 | Phase 3 | Bid to Award | Technical Scoring | Evaluation Committee Member | High | Functional | Candidate | SP4 | 1 | Submit technical scoring record | Stage is open and evaluator assigned | 1. Score criteria. 2. Submit record. | Evaluation record locks on submit and updates aggregation candidate. | FSD 3.3.6 | Not Run
P3-017 | Phase 3 | Bid to Award | Peer Visibility | Evaluation Committee Member | Medium | Security | Manual-first | SP4 | 1 | Hide peer detailed scores during active scoring | Multiple evaluators exist | 1. Submit own record or not. 2. Attempt to view peer details. | Peer scores remain hidden until allowed stage/closure. | FSD 3.3.6 | Not Run
P3-018 | Phase 3 | Bid to Award | Financial Evaluation | Evaluation Committee Chair | High | Integration | Candidate | SP4 | 1/2 | System-calculate financial score from opened bid data | Financial stage is open | 1. Run financial evaluation. 2. Inspect score logic. | Financial score is derived consistently rather than manually typed. | FSD 3.3.6 | Not Run
P3-019 | Phase 3 | Bid to Award | Disqualification | Evaluation Committee Chair | High | Control | Candidate | SP4 | 1/2 | Create disqualification record for mandatory failure | Bid fails a mandatory requirement | 1. Confirm disqualification. 2. Review aggregation outcome. | Disqualification record exists and bid is excluded from later stages. | FSD 3.3.6 | Not Run
P3-020 | Phase 3 | Bid to Award | Evaluation Report | Evaluation Committee Chair | Critical | Functional | Candidate | SP4 | 1/2 | Generate evaluation report after required stages complete | Stages complete and records submitted | 1. Generate report. 2. Review recommendation summary. | Report compiles ranked results and disqualification summary. | FSD 3.3.6 | Not Run
P3-021 | Phase 3 | Bid to Award | Evaluation Report | Evaluation Committee Chair | Critical | Functional | Candidate | SP4 | 1/2 | Submit evaluation report to award stage | Draft report exists | 1. Submit report. | Evaluation session status updates and award draft can be created. | FSD 3.3.6 / AT-EVAL-001 | Not Run
P3-022 | Phase 3 | Bid to Award | Separation of Duty | Evaluation Committee Member | Critical | Security | Candidate | SP4 | 1/2 | Block evaluator from final award approval on same tender | Evaluator also has award role | 1. Attempt final award approval. | Action is blocked by separation-of-duty rules. | Phase 4 RBAC | Not Run
P3-023 | Phase 3 | Bid to Award | Award Decision | Head of Procurement | High | Functional | Candidate | SP4 | 1 | Create award decision from submitted evaluation report | Submitted evaluation report exists | 1. Generate draft award decision. | Award decision inherits recommendation and outcome lines. | FSD 3.3.7 | Not Run
P3-024 | Phase 3 | Bid to Award | Final Approval | Accounting Officer | Critical | Functional | Candidate | SP4 | 1/2 | Final approve award as authorized authority | Draft award decision exists | 1. Review award. 2. Final approve. | Award moves to approved state and downstream notifications/standstill can proceed. | FSD 3.3.7 / AT-AWD-001 | Not Run
P3-025 | Phase 3 | Bid to Award | Deviation Control | Accounting Officer | Critical | Control | Candidate | SP4 | 1/2 | Require deviation record when approved supplier differs from recommendation | Deviation scenario exists | 1. Change approved supplier. 2. Attempt final approval. | System requires formal deviation record before approval completes. | FSD 3.3.7 | Not Run
P3-026 | Phase 3 | Bid to Award | Notifications | Procurement Officer | High | Functional | Hybrid | SP4 | 0 | Generate successful and unsuccessful bidder notifications | Approved award exists | 1. Trigger notifications. 2. Review output records. | Notification records are created with delivery status fields. | FSD 3.3.7 | Not Run
P3-027 | Phase 3 | Bid to Award | Standstill | Accounting Officer | High | Control | Candidate | SP4 | 1/2 | Initialize standstill period after award notification | Standstill-required award exists | 1. Approve award and send notifications. | Standstill record is created with correct dates and contract readiness remains blocked. | FSD 3.3.7 | Not Run
P3-028 | Phase 3 | Bid to Award | Complaint Hold | Complaint Review Chair | Critical | Integration | Candidate | SP6 | 1/2 | Block contract readiness when complaint hold is active | Award in standstill and complaint submitted | 1. Apply complaint hold. 2. Review award readiness. | Award is not ready for contract while hold remains active. | FSD 3.3.7 / 3.3.10 | Not Run
P3-029 | Phase 3 | Bid to Award | Audit | Auditor / Oversight User | High | Audit | Candidate | SP4 | 1/2 | Verify opening, evaluation and award audit chain | Opening, evaluation and award actions completed | 1. Filter audit events by tender/award. | High-risk events are complete and attributable. | Phase 4 Audit | Not Run
P3-030 | Phase 3 | Bid to Award | Portal Security | Supplier User | Medium | Security | Manual-first | SP4 | 1 | Restrict supplier to own notifications only | Multiple suppliers notified | 1. Log in as supplier A. 2. Open notifications. | Supplier sees only own records and cannot access competitor outputs. | Phase 4 RBAC | Not Run
P4-001 | Phase 4 | Contract & Delivery | Contract Creation | Procurement Officer | High | Functional | Candidate | SP5 | 1 | Create contract from approved award | Award is approved and contract-ready | 1. Trigger Create Contract from award. | Contract draft is created with inherited source context. | FSD 3.3.8 / AT-CON-001 | Not Run
P4-002 | Phase 4 | Contract & Delivery | Standstill Control | Procurement Officer | Critical | Negative | Candidate | SP6 | 1/2 | Block contract creation while standstill or hold is active | Award is not contract-ready | 1. Attempt Create Contract. | System blocks creation until legal readiness is achieved. | FSD 3.3.8 | Not Run
P4-003 | Phase 4 | Contract & Delivery | Contract Approval | Head of Procurement | High | Functional | Candidate | SP5 | 1 | Approve contract draft through formal route | Draft contract exists | 1. Submit and approve contract. | Approval record is created and contract moves to Pending Signature. | FSD 3.3.8 | Not Run
P4-004 | Phase 4 | Contract & Delivery | Signing | Supplier User | High | Functional | Hybrid | SP5 | 1 | Complete supplier-side signature action | Contract sent for signature | 1. Open supplier contract task. 2. Sign/acknowledge as configured. | Signing record captures supplier action. | FSD 3.3.8 | Not Run
P4-005 | Phase 4 | Contract & Delivery | Activation | Procurement Officer | Critical | Control | Candidate | SP5 | 1/2 | Block contract activation before signing is complete | Contract pending signature exists | 1. Attempt Activate Contract. | Activation is blocked until signing record is complete. | FSD 3.3.8 | Not Run
P4-006 | Phase 4 | Contract & Delivery | Activation | Procurement Officer | Critical | Functional | Candidate | SP5 | 1/2 | Activate contract after successful signing | Signed contract exists | 1. Record completed signature. 2. Activate contract. | Contract moves to Active and status event is created. | FSD 3.3.8 | Not Run
P4-007 | Phase 4 | Contract & Delivery | Milestones | Contract Manager | High | Functional | Candidate | SP5 | 0 | View milestones and deliverables on active contract | Active contract exists | 1. Open contract. | Milestones and deliverables are visible and linked to execution plan. | FSD 3.3.8 | Not Run
P4-008 | Phase 4 | Contract & Delivery | Variation Request | Contract Manager | High | Functional | Candidate | SP5 | 1 | Create time-extension variation request | Active contract exists | 1. Create variation request for time extension. | Variation record captures requested change and before/after values. | FSD 3.3.8 | Not Run
P4-009 | Phase 4 | Contract & Delivery | Variation Budget Check | Finance Approver | Critical | Integration | Candidate | SP5 | 1/2 | Require budget validation for value-increase variation | Value increase variation exists | 1. Attempt approval/apply. | Budget validation executes before value increase can apply. | FSD 3.3.8 | Not Run
P4-010 | Phase 4 | Contract & Delivery | Variation Apply | Procurement Officer | High | Integration | Candidate | SP5 | 1/2 | Apply approved variation and update contract | Approved variation exists | 1. Apply variation. 2. Review contract values/dates. | Contract controlled fields update through service path and status event is logged. | FSD 3.3.8 | Not Run
P4-011 | Phase 4 | Contract & Delivery | Inspection Creation | Inspection Officer | High | Functional | Candidate | SP5 | 0 | Create inspection from active contract scope | Active contract with deliverable exists | 1. Create inspection from milestone/deliverable. | Inspection record is created with correct contract linkage. | FSD 3.3.9 | Not Run
P4-012 | Phase 4 | Contract & Delivery | Inspection Templates | Inspection Officer | High | Functional | Candidate | SP5 | 0 | Apply inspection method template to inspection | Inspection exists and templates seeded | 1. Apply template. | Checklist/parameter lines populate inspection from template. | FSD 3.3.9 / Revised | Not Run
P4-013 | Phase 4 | Contract & Delivery | Checklist Inspection | Inspection Officer | High | Functional | Candidate | SP5 | 0 | Record checklist inspection results | Inspection exists | 1. Complete checklist lines. 2. Save. | Checklist outcomes are stored and contribute to inspection result. | FSD 3.3.9 | Not Run
P4-014 | Phase 4 | Contract & Delivery | Parameter Testing | Inspection Officer | Critical | Functional | Candidate | SP5 | 0/1 | Record parameter test results within tolerance | Parameter-based inspection exists | 1. Enter measured values. 2. Save. | System evaluates result against tolerance and marks parameter passed. | FSD 3.3.9 Revised / AT-INSP-001 | Not Run
P4-015 | Phase 4 | Contract & Delivery | Non-Conformance | Inspection Officer | Critical | Control | Candidate | SP5 | 1 | Create non-conformance for failed critical parameter | Parameter result fails tolerance | 1. Save failed result. 2. Review inspection. | Non-conformance record is created and linked to inspection. | FSD 3.3.9 Revised | Not Run
P4-016 | Phase 4 | Contract & Delivery | Acceptance Control | Inspection Officer | Critical | Negative | Candidate | SP5 | 1/2 | Block full acceptance when critical NCR remains unresolved | Inspection has critical NCR | 1. Attempt full acceptance. | System blocks full acceptance and requires corrective path or waiver. | FSD 3.3.9 | Not Run
P4-017 | Phase 4 | Contract & Delivery | Partial Acceptance | Contract Manager | High | Control | Candidate | SP5 | 1/2 | Allow partial acceptance with tracked open issues | Inspection result is partial with non-critical issues | 1. Submit partial acceptance decision. | Accepted scope is recorded and open issues remain tracked. | FSD 3.3.9 | Not Run
P4-018 | Phase 4 | Contract & Delivery | Reinspection | Inspection Officer | High | Control | Candidate | SP5 | 1 | Create reinspection after corrective action | Original inspection or NCR exists | 1. Create reinspection. 2. Link follow-up inspection. | Reinspection chain is preserved for auditability. | FSD 3.3.9 | Not Run
P4-019 | Phase 4 | Contract & Delivery | Payment Readiness | Contract Manager | Medium | Integration | Candidate | SP5 | 1 | Set payment readiness only after valid acceptance | Accepted output exists | 1. Review acceptance record. | Payment readiness signal shows Ready only after acceptance conditions are met. | FSD 3.3.9 | Not Run
P4-020 | Phase 4 | Contract & Delivery | Contract Progress | Contract Manager | Medium | Integration | Candidate | SP5 | 1 | Recalculate contract completion from accepted milestones | Accepted milestone exists | 1. Open contract after acceptance update. | Completion percent reflects accepted scope and status events. | FSD 3.3.8/3.3.9 | Not Run
P4-021 | Phase 4 | Contract & Delivery | Role Security | Inspection Officer | Medium | Security | Manual-first | SP5 | 1 | Prevent inspector from activating contract | Inspector role exists | 1. Attempt contract activation. | Action is blocked by permissions and separation of duties. | Phase 4 RBAC | Not Run
P4-022 | Phase 4 | Contract & Delivery | Audit | Auditor / Oversight User | High | Audit | Candidate | SP5 | 1/2 | Verify audit trail for contract activation, variation and acceptance | Contract lifecycle actions completed | 1. Filter audit trail by contract ID. | Critical events are captured and attributable. | Phase 4 Audit | Not Run
P4-023 | Phase 4 | Contract & Delivery | Field Measurement | Inspection Officer | High | Functional | Hybrid | SP5 | 0/1 | Record road works field measurement inspection parameters | Road works template exists in inspection methods | 1. Apply road works template. 2. Record width/thickness/compaction values. | Field measurements are stored against expected tolerances and produce pass/fail outcomes. | FSD 3.3.9 Revised | Not Run
P4-024 | Phase 4 | Contract & Delivery | Sampling & Lab | Inspection Officer | High | Functional | Hybrid | SP5 | 0/1 | Record pharma or lab sample with chain-of-custody | Sampling inspection template exists | 1. Create sample record. 2. Record chain of custody and lab ref. | Sample record is linked to inspection and ready for lab result capture. | FSD 3.3.9 Revised | Not Run
P4-025 | Phase 4 | Contract & Delivery | Lab Result Control | Inspection Officer | Critical | Control | Candidate | SP5 | 1/2 | Block full acceptance when mandatory lab result is inconclusive or failed | Sample/lab result exists | 1. Record failed or inconclusive lab result. 2. Attempt full acceptance. | Full acceptance remains blocked until resolution or approved waiver. | FSD 3.3.9 Revised | Not Run
P5-001 | Phase 5 | Governance, Complaints & Downstream | Deliberations | Head of Procurement | Medium | Functional | Manual-first | SP5 | 0 | Create deliberation session with agenda and attendance | Governance module available | 1. Create deliberation session. 2. Add agenda items and attendance. | Session is recorded with linked procurement object. | FSD 3.3.11 | Not Run
P5-002 | Phase 5 | Governance, Complaints & Downstream | Deliberations | Head of Procurement | Medium | Functional | Manual-first | SP5 | 0 | Record minutes, recommendation and resolution | Deliberation session exists | 1. Enter minute text. 2. Add recommendation. 3. Add resolution. | Minutes, recommendation and resolution are stored as distinct records. | FSD 3.3.11 | Not Run
P5-003 | Phase 5 | Governance, Complaints & Downstream | Deliberations | Procurement Officer | Low | Control | Manual-first | SP5 | 0 | Track follow-up action from deliberation resolution | Resolution exists | 1. Create follow-up action. 2. Assign owner and due date. | Follow-up action is visible and trackable. | FSD 3.3.11 | Not Run
P5-004 | Phase 5 | Governance, Complaints & Downstream | Complaints | Supplier User | Critical | Functional | Hybrid | SP6 | 0 | Submit complaint with evidence against award | Award in standstill exists | 1. File complaint. 2. Upload evidence. 3. Submit. | Complaint gets business ID and enters admissibility review. | FSD 3.3.10 / AT-CMP-001 | Not Run
P5-005 | Phase 5 | Governance, Complaints & Downstream | Complaints | Complaint Review Chair | Critical | Functional | Candidate | SP6 | 1 | Perform admissibility review | Submitted complaint exists | 1. Open complaint. 2. Mark admissible or inadmissible. | Admissibility status is recorded with reasoning. | FSD 3.3.10 | Not Run
P5-006 | Phase 5 | Governance, Complaints & Downstream | Hold Logic | Complaint Review Chair | Critical | Integration | Candidate | SP6 | 1/2 | Apply award or contract hold from complaint | Complaint affects procurement progression | 1. Apply hold. | Hold status changes and affected object becomes blocked from progression. | FSD 3.3.10 | Not Run
P5-007 | Phase 5 | Governance, Complaints & Downstream | Review Panel | Complaint Review Member | High | Functional | Manual-first | SP6 | 1 | Assign complaint review panel and capture review notes | Admissible complaint exists | 1. Assign panel members. 2. Add review notes. | Review assignments and records are captured. | FSD 3.3.10 | Not Run
P5-008 | Phase 5 | Governance, Complaints & Downstream | Complaint Decision | Complaint Review Chair | Critical | Functional | Candidate | SP6 | 1/2 | Issue complaint decision with remedy | Review records exist | 1. Draft decision. 2. Issue decision. | Decision is stored with reasoning and remedy details. | FSD 3.3.10 | Not Run
P5-009 | Phase 5 | Governance, Complaints & Downstream | Complaint Actions | Complaint Review Chair | Critical | Integration | Candidate | SP6 | 1/2 | Execute complaint remedy against linked procurement object | Complaint decision requires action | 1. Execute remedy. | Complaint action updates linked object through controlled service, not direct edit. | FSD 3.3.10 | Not Run
P5-010 | Phase 5 | Governance, Complaints & Downstream | Appeals | Complaint Review Chair | Medium | Control | Manual-first | SP6 | 1 | Create appeal record against complaint decision | Complaint decision exists | 1. Lodge appeal. 2. Save. | Appeal record links correctly to decision and complaint. | FSD 3.3.10 | Not Run
P5-011 | Phase 5 | Governance, Complaints & Downstream | Stores Receipt | Storekeeper | High | Functional | Candidate | SP7 | 0/1 | Create procurement goods receipt from accepted goods | Accepted goods-type output exists | 1. Create goods receipt from acceptance. 2. Record received quantities. | Goods receipt links to contract and acceptance and updates store state. | FSD 3.3.12 / AT-STORES-001 | Not Run
P5-012 | Phase 5 | Governance, Complaints & Downstream | Stores Issue | Storekeeper | High | Functional | Candidate | SP7 | 0/1 | Issue stocked items to department | Posted goods receipt exists | 1. Create store issue. 2. Record issued quantity and recipient. | Store issue reduces remaining balance and preserves traceability. | FSD 3.3.12 | Not Run
P5-013 | Phase 5 | Governance, Complaints & Downstream | Stores Reconciliation | Storekeeper | High | Control | Manual-first | SP7 | 0/1 | Flag stock variance during reconciliation | Stock variance scenario exists | 1. Run reconciliation. 2. Record actual stock count. | Stores Balance Exception is created with variance details. | FSD 3.3.12 | Not Run
P5-014 | Phase 5 | Governance, Complaints & Downstream | Assets | Asset Officer | High | Functional | Candidate | SP7 | 0/1 | Register procured asset from accepted/store-linked item | Assetizable item exists | 1. Register asset. 2. Assign asset tag. | Procured asset record links back to procurement source and tag is unique. | FSD 3.3.13 / AT-ASSET-001 | Not Run
P5-015 | Phase 5 | Governance, Complaints & Downstream | Asset Handover | Asset Officer | Medium | Functional | Manual-first | SP7 | 0/1 | Create handover and custody assignment | Procured asset exists | 1. Handover asset to department/user. 2. Record custody. | Custody assignment becomes active and handover history is preserved. | FSD 3.3.13 | Not Run
P5-016 | Phase 5 | Governance, Complaints & Downstream | Asset Movement | Asset Officer | Medium | Functional | Manual-first | SP7 | 0/1 | Record asset movement on transfer | Asset exists | 1. Transfer asset location. 2. Record movement. | Movement record is added to lifecycle history. | FSD 3.3.13 | Not Run
P5-017 | Phase 5 | Governance, Complaints & Downstream | Asset Disposal | Asset Officer | High | Control | Manual-first | SP7 | 1 | Require approval for asset disposal | Asset marked for retirement/disposal | 1. Create disposal record. 2. Attempt completion without approval. | System requires approval before disposal can complete. | FSD 3.3.13 | Not Run
P5-018 | Phase 5 | Governance, Complaints & Downstream | Role Separation | Storekeeper | Medium | Security | Manual-first | SP7 | 1 | Prevent storekeeper from registering assets without asset role | Storekeeper user exists | 1. Attempt asset registration. | Action is blocked by role permissions. | Phase 4 RBAC | Not Run
P5-019 | Phase 5 | Governance, Complaints & Downstream | Role Separation | Asset Officer | Medium | Security | Manual-first | SP7 | 1 | Prevent asset officer from creating goods receipt without stores role | Asset officer user exists | 1. Attempt goods receipt creation. | Action is blocked by role permissions. | Phase 4 RBAC | Not Run
P5-020 | Phase 5 | Governance, Complaints & Downstream | Oversight UI | Auditor / Oversight User | Low | UX | Manual-first | SP6 | 0 | Audit & Oversight workspace surfaces complaints, exceptions and deviations | Workspace implemented | 1. Open Audit & Oversight. | Workspace shows complaint impact, exceptions, deviations and risk views. | WS-010 | Not Run
X-001 | Cross-Phase | Cross-Phase Controls | Traceability | Auditor / Oversight User | Critical | Integration | Candidate | SP1-SP7 | 1/2 | Trace end-to-end lineage from strategy to acceptance | Linked seeded data exists across packs | 1. Start at Performance Target. 2. Traverse budget, requisition, plan, tender, award, contract and acceptance links. | Lineage is complete and each stage references the upstream source path. | Phase 5 Canonical Model | Not Run
X-002 | Cross-Phase | Cross-Phase Controls | Entity Scope | Requisitioner | Critical | Security | Manual-first | SP1-SP7 | 1/2 | Prevent cross-entity access to transactional records | Two-entity seed data exists | 1. Log in as entity-scoped user. 2. Attempt to open other-entity record. | Access is hidden or blocked by entity scoping controls. | Phase 4 RBAC | Not Run
X-003 | Cross-Phase | Cross-Phase Controls | Admin Restriction | System Administrator | Critical | Security | Manual-first | SP3 | 2 | Do not rely on System Administrator to bypass sealed bid restrictions | Sealed bid exists | 1. Attempt raw access as admin. 2. Review result. | Sensitive access remains controlled/audited rather than casually open. | Phase 4 RBAC | Not Run
X-004 | Cross-Phase | Cross-Phase Controls | Sensitive Access Audit | Auditor / Oversight User | Critical | Audit | Candidate | SP3 | 2 | Audit allowed and denied access to sensitive files | Sensitive access helper is implemented | 1. Trigger one allowed and one denied access. 2. Review audit entries. | Audit captures both allowed and denied sensitive-access events. | Phase 4 Audit | Not Run
X-005 | Cross-Phase | Cross-Phase Controls | Notifications | System Administrator | Medium | Functional | Hybrid | BASE-REF | 0 | Render notification templates with business placeholders | Templates and events exist | 1. Trigger template rendering for test event. | Rendered notification includes expected placeholders and no broken tokens. | Phase 4 Notification | Not Run
X-006 | Cross-Phase | Cross-Phase Controls | Numbering | System Administrator | Medium | Configuration | Candidate | BASE-REF | 0 | Apply numbering policies consistently across doctypes | Policies and multiple doctypes exist | 1. Create records across modules. | Business IDs follow scoped numbering patterns consistently. | Wave 0 Core | Not Run
X-007 | Cross-Phase | Cross-Phase Controls | My Work Workspace | System Administrator | Medium | UX | Manual-first | SP1-SP7 | 0 | Show pending tasks by role in My Work workspace | Multiple seeded work queues exist | 1. Log in as several personas. 2. Open My Work. | Each role sees pending approvals/assignments relevant to them. | WS-001 | Not Run
X-008 | Cross-Phase | Cross-Phase Controls | Search & Reports | Supplier User | Medium | Security | Manual-first | SP3-SP6 | 1 | Show role-appropriate search/report results only | Seeded data exists across portal/internal | 1. Search for key objects as supplier/internal users. | Results are filtered appropriately by role and scope. | Phase 4 RBAC | Not Run
X-009 | Cross-Phase | Cross-Phase Controls | Seed Reset | System Administrator | Medium | Data | Manual-first | SP1-SP7 | 0 | Reload deterministic UAT seed packs with stable IDs | Seed commands exist | 1. Reset chosen scenario. 2. Verify business IDs. | Seed loaders recreate expected records deterministically. | UAT Seed Pack | Not Run
X-010 | Cross-Phase | Cross-Phase Controls | Audit Export | Auditor / Oversight User | High | Reporting | Manual-first | SP1-SP7 | 1/2 | Export high-risk audit events for review | High-risk actions have occurred | 1. Run audit export/report. | Report includes reservations, bid opening, award approvals, complaint holds, and activations. | Phase 4 Audit | Not Run
X-011 | Cross-Phase | Cross-Phase Controls | Public Transparency | Auditor / Oversight User | High | Security | Manual-first | SP3-SP7 | 1 | Exclude sealed/confidential content from transparency output | Public output/report exists | 1. Open transparency outputs. | Only public-approved tender/award/contract summaries are shown. | Phase 4 Reporting | Not Run
X-012 | Cross-Phase | Cross-Phase Controls | Exceptions | Finance Approver | Critical | Control | Candidate | SP1-SP6 | 2 | Require exception record for emergency override path | Emergency or override scenario exists | 1. Attempt override without exception. 2. Retry with approved exception. | Override is blocked without exception and allowed only through controlled exception path. | Wave 0 Exception | Not Run
X-013 | Cross-Phase | Cross-Phase Controls | Governance Integrity | Head of Procurement | Medium | Control | Manual-first | SP5-SP6 | 1 | Ensure deliberation records do not replace formal approval records | Deliberation and approval records both exist | 1. Review linked records. | Deliberations complement but do not overwrite transactional approvals. | FSD 3.3.11 / Phase 4 | Not Run
X-014 | Cross-Phase | Cross-Phase Controls | Stores-to-Assets Handoff | Asset Officer | Medium | Integration | Candidate | SP7 | 1 | Preserve procurement source traceability from stores receipt into asset record | Store-linked assetizable item exists | 1. Register asset from store-linked item. 2. Review source links. | Asset preserves source goods receipt, acceptance and contract references. | FSD 3.3.12 / 3.3.13 | Not Run
X-015 | Cross-Phase | Cross-Phase Controls | Complaint Release | Complaint Review Chair | High | Integration | Candidate | SP6 | 1/2 | Release complaint hold only through controlled decision action | Hold is active on award | 1. Attempt ad hoc hold removal. 2. Release through complaint decision workflow. | Ad hoc hold removal is blocked; controlled release updates affected object correctly. | FSD 3.3.10 | Not Run
X-016 | Cross-Phase | Cross-Phase Controls | Multi-lot Award Traceability | Accounting Officer | Medium | Integration | Manual-first | SP3-SP4 | 1 | Maintain lot-specific award outcomes where multi-lot tender is used | Multi-lot tender seed exists | 1. Complete multi-lot evaluation. 2. Review award outcome lines. | Award outcome lines preserve lot-level result traceability. | FSD 3.3.7 | Not Run

## Coverage_Matrix
Coverage Matrix
Formula-driven counts by role and phase, sourced from the Detailed Test Cases sheet.
Role | Phase 1 | Phase 1.5 | Phase 2 | Phase 3 | Phase 4 | Phase 5 | Cross-Phase | Total Cases | Critical Cases | High Cases
Planning Authority | 4 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 2 | 3
Strategy Manager | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3
Budget Officer | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 4 | 6
Finance Approver | 6 | 4 | 0 | 0 | 1 | 0 | 1 | 12 | 8 | 4
Requisitioner | 0 | 9 | 0 | 0 | 0 | 0 | 1 | 10 | 3 | 5
Head of Department | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 2
Procurement Officer | 0 | 6 | 20 | 2 | 5 | 1 | 0 | 34 | 9 | 21
Head of Procurement | 0 | 0 | 3 | 1 | 1 | 2 | 1 | 8 | 2 | 3
Supplier Registration Officer | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1
Opening Committee Chair | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3 | 2 | 1
Opening Committee Member | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1
Evaluation Committee Member | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 5 | 2 | 2
Evaluation Committee Chair | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 2 | 2
Accounting Officer | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 4 | 2 | 1
Contract Manager | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 5 | 0 | 3
Inspection Officer | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 11 | 4 | 6
Complaint Review Chair | 0 | 0 | 0 | 1 | 0 | 5 | 1 | 7 | 5 | 1
Complaint Review Member | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1
Storekeeper | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 3
Asset Officer | 0 | 0 | 0 | 0 | 0 | 5 | 1 | 6 | 0 | 2
Auditor / Oversight User | 2 | 1 | 1 | 1 | 1 | 1 | 4 | 11 | 2 | 7
System Administrator | 3 | 1 | 0 | 1 | 0 | 0 | 5 | 10 | 2 | 0
Supplier User | 0 | 0 | 1 | 8 | 1 | 1 | 1 | 12 | 3 | 6
Total Cases by Phase | 30 | 25 | 27 | 30 | 25 | 20 | 16 | 173 | 53 | 84

## UAT_Run_Log
UAT Run Log
Template for execution cycles, by journey, role, seed pack, or module.
Cycle | Environment | Start Date | End Date | Tester | Role | Scope / Filter | Executed Cases | Pass | Fail | Blocked | Notes | Defect IDs

## Defect_Log
Defect Log
Template for defect triage and evidence capture during UAT and regression.
Defect ID | Linked Test ID | Phase | Module | Severity | Priority | Status | Reported By | Date Raised | Assigned To | Environment | Summary | Actual Behaviour | Expected Behaviour | Workaround | Resolution Notes

## Sources
Sources
Design basis used for this workbook
Primary design basis | KenTender modular solution design developed in this project thread covering Strategy, Budget, Requisition, Planning, Tender, Bid Submission, Opening, Evaluation, Award, Contract, Inspection, Deliberations, Complaints, Stores, Assets, cross-cutting architecture, UAT workspaces, and seed-pack planning.
Implementation target | Frappe / ERPNext-based modular implementation using explicit service actions, role-based workspaces, entity scoping, audit events, and seed-driven UAT.
Usage note | Tune doctype names, workflow labels, queue filters, and supplier portal labels to the exact implementation deployed in QA/UAT before formal signoff.